**On Board with Me Project**

Program Update

May 2019

|  |  |  |
| --- | --- | --- |
| **STAKEHOLDER** | **STRATEGY** | **DELIVERABLES** |
| PWdWA | Provide project management and oversight to deliver project planned outcomes within budget | Delivered | * Register of Board and CEO contacts in the disability sector
* Stakeholder Mapping and Management Plan
* Project Reference Group
* Board Disability Diversity Survey Report
* Board Disability Diversity Guide for Employers
 |
| On-Track | * Board Disability Diversity Guide for Candidates
* Board Candidate Resume template
* Board Diversity Policy template
 |
| Candidates | Identify Board candidates. Connect candidates with Board training opportunities. Develop Candidate Development pipeline | Delivered | * Board Candidate Register
* Disability Leaders group briefings
* LinkedIn training
* Risk management and governance briefing
* Board Disability Survey results briefing
* Board Directors Breakfast – How to get appointed
* Aspiring Board Director training
* Disability Aspiring Leaders LinkedIn Group
* Board Effectiveness training for current Board members
* Board Disability Diversity Strategy Workshop
 |
| On-Track | * Board Candidate Networking Sundowner
 |

|  |  |  |
| --- | --- | --- |
| **STAKEHOLDER** | **STRATEGY** | **DELIVERABLES** |
| Leadership & Governance Organisations | Define Board competency requirements. Identify and connect candidates with training and development opportunities | Delivered | * Board Candidate Competency requirements Training program options reviewed
* Leadability Training Presentations
* Promotion of training course options, training sponsorship and scholarships to Candidates
 |
| Government | Integrate OBM objectives with OnBoardWA register and program to improve disability diversity of government Boards | Delivered | * OnBoardWA Register integration with project
 |
| On-Track | * Board Disability Diversity Guides and Reports published on OnBoardWA website
 |
| Disability Sector Boards | Understand current Board representation, and barriers to appointment of people with disability to NFP Boards.Develop Sector-wide improvement strategies | Delivered | * Board Disability Diversity Survey of WA Sector
* Board Disability Diversity Strategy Workshop
 |
| On-Track | * Board Disability Diversity Breakfast event
 |